## Risk Assessment
Risk Assessment Checklist
Identify what could go wrong, score it, and plan how you'll respond. Add rows as needed.
From: Project Management Made Simple · identityquartet.github.io/project-mgt-guide
Project name
Prepared by |  |  | Date
How to score
Rating | Likelihood (how likely is it?) |  |  | Impact (how serious if it happens?)
1 — Low | Unlikely to happen |  |  | Minor inconvenience, easy to absorb
2 — Medium | Could happen |  |  | Noticeable disruption to scope/budget/timeline
3 — High | Likely to happen |  |  | Major disruption — could derail the project
Risk register
Score = Likelihood × Impact (1–9). Anything 6 or higher needs an owner and a clear mitigation.
# | Risk | Likelihood (1-3) | Impact (1-3) | Score | Mitigation / response | Owner | Status
1 | Key team member becomes unavailable | 2 | 3 | 6 | Cross-train someone else; document key tasks; identify backup volunteer. | Project lead | Open
2 | Budget overrun on supplier costs | 2 | 2 | 4 | Get 3 quotes; agree fixed-price contract where possible; hold 10% contingency. | Finance lead | Open
3 | Low engagement / poor turnout | 2 | 3 | 6 | Confirm audience need before launch; promote 4+ weeks ahead; build email list early. | Comms lead | Open
4 | Technology/website fails on launch day | 1 | 3 | 3 | Test 1 week prior; have manual backup process; identify support contact. | Tech lead | Open
5 | Regulatory / GDPR compliance gap | 2 | 3 | 6 | Review against Charities Regulator + DPC guidance early; appoint named DP officer. | Governance lead | Open
6
7
8
9
10
11
12
13
14
15
Review schedule
How often will you review this register? |  |  |  | e.g. weekly / fortnightly / monthly
Notes
Risks marked High likelihood × High impact (score 9) need immediate attention before the project starts. Don't proceed without a mitigation plan.