## Register
Stakeholder Mapping Tool
List every person or group your project affects, then classify by Power × Interest to plan how you'll engage each one.
From: Project Management Made Simple · identityquartet.github.io/project-mgt-guide
Project name
Prepared by |  |  | Date
How to score
Score | Power (their ability to influence the project) |  |  |  | Interest (how much they care about the outcome)
1 — Low | Little ability to influence decisions |  |  |  | Doesn't follow the project closely
2 — Medium | Some influence, especially in their area |  |  |  | Pays attention; reacts to updates
3 — High | Can approve, block, or fundamentally shape it |  |  |  | Personally invested in the outcome
Engagement strategy by quadrant
Power | Interest | Approach |  | What it means in practice
Low (1) | Low (1) | Monitor |  | Keep informed at minimum — light updates only
Low (1) | High (2-3) | Keep informed |  | Regular updates; they care even if they can't change much
High (2-3) | Low (1) | Keep satisfied |  | Don't ignore — bring them along; major decisions need a heads-up
High (2-3) | High (2-3) | Manage closely |  | Top priority — frequent contact, deep involvement, no surprises
Stakeholder register
# | Name / group | Their interest in the project | Power (1-3) | Interest (1-3) | Quadrant | Approach | Comms channel | Frequency | Owner
1 | Board / Trustees | Accountability for outcomes; reputation | 3 | 3 | Manage closely | Direct contact | Email + meeting | Monthly | Project lead
2 | Funder (Pobal / LEO) | Conditions of grant; reporting requirements | 3 | 3 | Manage closely | Reports + check-ins | Email + report | Quarterly | Project lead
3 | Beneficiaries / customers | Direct impact on their experience | 1 | 3 | Keep informed | User updates | Email + social | Monthly | Comms lead
4 | Volunteers / staff | Day-to-day workload and morale | 2 | 3 | Manage closely | Team channels | Slack / WhatsApp | Weekly | Team lead
5 | Suppliers / partners | Contract delivery and payment | 2 | 1 | Keep satisfied | Contract owner | Email | As needed | Procurement
6
7
8
9
10
11
12
13
14
15
Tip
Re-run this exercise at major project milestones — stakeholder power and interest shift over time, especially as a project moves from planning to delivery.